## Blad1
ID Code | Type | Group | Priority | Est. Time | ID Code Number | ID Code Description | Category | Assets Overview |  | Sprint 1 (19-09 t/m 02-10) | Sprint 2 (03-10 t/m 16-10) | Vakantie (17-10 t/m 23-10) | Sprint 3 (24-10 t/m 06-11) | Sprint 4 (07-11 t/m 20-11) | DEADLINE PROTOTYPE (21-11 t/m 27-11) | Sprint 5 (28-11 t/m 11-12) | Sprint 6 (12-12 t/m 25-12) | Vakantie (26-12 t/m 08-01) | Sprint 7 (09-01 t/m 22-01) | DEADLINE EIND (23-01 t/m 29-01)
1C_Gaijin_01 | Concept Art | A | 10 | 0 | Concept Art | A. Character | A. Character | Gaijin ¦ Ninja |  | Artist | Artist | Artist | Artist | Artist | Artist | Artist | Artist | Artist | Artist | Artist
3D_Gaijin_01 | Modeling | A | 10 | 10 | Modeling | B. Enemy | A. Character (NPC) | Dragon ¦ Priest ¦ Villagers ¦ Ghost |  | Dragon (56) | Priest (39) |  | Shrine (27) | StoneWall (14) |  | House04 (28) | MarketStall (32) |  | Bob (50)
4U_Gaijin_01 | Unwrap | A | 10 | 5 | Unwrap | C. Weapon | A. Character (Extra) | Bob the Goat ¦ Teletubby in Kimono ¦ Koi |  | Samurai (50) | Bandit (44) |  | Katana (13) | Demon (40) | 22-11 PRESENTATIE | SmallWoodenFence (10) | Crate (3) |  | Teletubby (34) | 24-01 PRESENTATIE
2D_Gaijin_01 | Texture | A | 10 | 8 | Texture | D. Building | B. Enemy | Samurai ¦ Bandit ¦ Guard ¦ Warlord ¦ Demon |  | Warlord (59) | Prison (37) |  | Shuriken (10) | WoodenCage (17) |  | Pillar (5) | WallScroll (6)
5R_Gaijin_01 | Rigging | A | 10 | 6 | Rigging | E. Decoration | C. Weapon | Katana ¦ Shuriken ¦ Smoke Bombs ¦ Kusarigama ¦ Nunchaku ¦ Fan ¦ Darts |  | Palace (40) | House01 (33) |  | Ninja (42) | Chain (3) |  | Intro (20) | WallArt (14)
6A_Gaijin_01 | Animation | A | 10 | 8 | Animation | F. Nature | C. Weapon (Decor) | Katana ¦ Bamboo Sword ¦ Small Katana ¦ Throwing Knives ¦ Bo Staff |  | Gaijin (46) | House02 (28) |  | SmokeBomb (4) | Throne (13) |  | Temple (20) | SittingTable (5)
8SOU_Gaijin_01 | Sound | A | 10 | 9 | Script | G. Particles | D. Building (Village) | House (x4) ¦ Market Stall ¦ Shrine ¦ Prison ¦ Palace ¦ Dojo |  |  | Kusarigama (32) |  | Bridge (36) | Water (0) |  | Dragon (20) | Scroll (5)
[5 empty] | Sound | H. HUD | D. Building (Spirit World) | Cottage |  |  |  |  | Guard (46) | Fire (0) |  | End (20) | WallScrollPainting (8)
1C_Ninja_02 | Concept Art | A | 9 | 5 | Particles | I. Script | E. Decoration (Village) | Torii ¦ Stone Lantern ¦ Crates ¦ Lanterns ¦ Stone Wall ¦ Signs ¦ Small Wooden Fence ¦ Bridges |  |  |  |  | Dojo (37) | Nunchaku (21) |  | Villager (39) | Koi (31)
3D_Ninja_02 | Modeling | A | 9 | 4 |  |  | E. Decoration (Spirit World) | Torii ¦ Lanterns ¦ Flags |  |  |  |  | Torii (13) | Fan (38) |  | Ghost (6) | Cottage (30)
4U_Ninja_02 | Unwrap | A | 9 | 5 |  |  | E. Decoration (House) | Paper Lanterns ¦ Rag Lines ¦ Futon ¦ Bucket ¦ Fire Place ¦ Bonsai |  |  |  |  | StoneLantern (8) | Dart (13) |  | SmallKatana (6) | SpirLantern (4)
2D_Ninja_02 | Texture | A | 9 | 6 |  |  | E. Decoration (Prison) | Wooden Cages ¦ Chains ¦ Tables ¦ Candles ¦ Chairs ¦ Crates | [5 empty] | VilLantern (4) |  | ThrowingKnife (5) | Flag (6)
5R_Ninja_02 | Rigging | A | 9 | 6 |  |  | E. Decoration (Palace) | Wall Scrolls ¦ Vase ¦ Statues ¦ Lanterns ¦ Wall Art ¦ Pillows ¦ Sitting Table ¦ Pillars ¦ Decorated Pillars ¦ Throne ¦ Scroll ¦ Tea Set ¦ Side Table | [5 empty] | PaperLantern (4) |  | Ragline (6) | Bonsai (19)
6A_Ninja_02 | Animation | A | 9 | 9 |  |  | E. Decoration (Dojo) | Wooden Dummies ¦ Weapon Racks ¦ Wall Scrolls/Paintings | [5 empty] | Table (5) |  | Chair (5) | Statue (22)
8SOU_Ninja_02 | Sound | A | 9 | 7 |  |  | F. Nature (Vegetation) | Trees ¦ Flowers ¦ Cherry Blossom Tree ¦ Bush ¦ Grass ¦ Plant ¦ Lily | [5 empty] | Candle (3) |  | PalLantern (4) | Pillow (4)
[7 empty] | F. Nature (Landscape) | Cave ¦ Stone (with moss) |  | 251 | 213 |  | 236 | DecoratedPillar (11) |  | Weaponrack (10) | SideTable (3)
1C_Dragon_03 | Concept Art | A | 10 | 0 |  |  | G. Particles | Mist ¦ Blossom Leaves ¦ Smoke ¦ Water ¦ Fire ¦ Hit/Strike ¦ Blood ¦ Punch ¦ Jump ¦ Dragon ¦ Abilities ¦ Smoke Bomb | [5 empty] | Dummy (8) |  | Smoke (0) | Futon (6)
3D_Dragon_03 | Modeling | A | 10 | 10 |  |  | H. HUD | Start Menu ¦ Ingame Menu ¦ HUD ¦ Inventory ¦ Quest Log ¦ Map ¦ Loading Screen | [5 empty] | Punch (5) |  | Blood (5) | Bucket (4)
4U_Dragon_03 | Unwrap | A | 10 | 8 |  |  | H. HUD (Cutscenes) | Intro ¦ Temple ¦ Dragon ¦ End | [5 empty] | Jump (3) |  | Sign (7) | Vase (5)
2D_Dragon_03 | Texture | A | 10 | 10 |  |  | I. Script | AI ¦ PlayerController ¦ Wallfade ¦ Load Save ¦ Shrines ¦ Settings ¦ Events | [5 empty] | House03 (28) |  | Fireplace (12) | TeaSet (11)
5R_Dragon_03 | Rigging | A | 10 | 9 |  |  | I. Script (Managers) | Eventmanager ¦ Player Attackmanager ¦ Music Sound Manager ¦ Menu Manager (Main Menu & Ingame) ¦ Load Save Manager ¦ Combat Manager | [7 empty] | Blossomleaves (4) | Stone (8) |  |  |  | Totaal
6A_Dragon_03 | Animation | A | 10 | 10 |  |  | I. Script (Optional) | Co-op | Victoria | [6 empty] | 232 | 226 |  | 84
8SOU_Dragon_03 | Sound | A | 10 | 9 |  |  |  |  | Jay |  |  |  |  | 230
Gerwin
1C_Priest_04 | Concept Art | A | 10 | 4 |  |  |  |  | René
3D_Priest_04 | Modeling | A | 10 | 8 |  |  |  |  | Nathaly
4U_Priest_04 | Unwrap | A | 10 | 5 | [17 empty] | Artists Totaal
2D_Priest_04 | Texture | A | 10 | 7
5R_Priest_04 | Rigging | A | 10 | 6
6A_Priest_04 | Animation | A | 10 | 5 | [5 empty] | Sprint 1 (19-09 t/m 02-10) | Sprint 2 (03-10 t/m 16-10) | Vakantie (17-10 t/m 23-10) | Sprint 3 (24-10 t/m 06-11) | Sprint 4 (07-11 t/m 20-11) | DEADLINE PROTOTYPE (21-11 t/m 27-11) | Sprint 5 (28-11 t/m 11-12) | Sprint 6 (12-12 t/m 25-12) | Vakantie (26-12 t/m 08-01) | Sprint 7 (09-01 t/m 22-01) | DEADLINE EIND (23-01 t/m 29-01)
8SOU_Priest_04 | Sound | A | 10 | 4 | [5 empty] | Development | Development | Development | Development | Development | Development | Development | Development | Development | Development | Development
[10 empty] | 7SCR_AI_01 | 7SCR_PlayerController_02 |  | 7SCR_Events_07 | 7SCR_LoadSave_04 |  | 7SCR_MenuManager_11 | 7SCR_Shrine_05 |  | 7SCR_Coop_14
1C_Villager_05 | Concept Art | A | 4 | 5 | [5 empty] | 7SCR_LoadSaveManager_12 | 7SCR_PlayerAttackManager_09 |  | 7SCR_EventManager_08 | 7SCR_CombatManager_13 |  | 7SCR_MusicSoundManager_10 | 7SCR_Settings_06
3D_Villager_05 | Modeling | A | 4 | 7
4U_Villager_05 | Unwrap | A | 4 | 5
2D_Villager_05 | Texture | A | 4 | 5
5R_Villagers_05 | Rigging | A | 4 | 6
6A_Villager_05 | Animation | A | 4 | 6 | [16 empty] | Totaal
8SOU_Villager_05 | Sound | A | 4 | 2
Wybren
6A_Ghost_06 | Animation | A | 4 | 4 | [17 empty] | Development Totaal
8SOU_Ghost_06 | Sound | A | 4 | 2
1C_Bob_07 | Concept Art | A | 1 | 7
3D_Bob_07 | Modeling | A | 1 | 5
4U_Bob_07 | Unwrap | A | 1 | 6
2D_Bob_07 | Texture | A | 1 | 8
5R_Bob_07 | Rigging | A | 1 | 6
6A_Bob_07 | Animation | A | 1 | 6
8SOU_Bob_07 | Sound | A | 1 | 2
3D_Teletubby_08 | Modeling | A | 1 | 5
4U_Teletubby_08 | Unwrap | A | 1 | 6
2D_Teletubby_08 | Texture | A | 1 | 7
5R_Teletubby_08 | Rigging | A | 1 | 6
6A_Teletubby_08 | Animation | A | 1 | 3
8SOU_Teletubby_08 | Sound | A | 1 | 2
3D_Koi_09 | Modeling | A | 2 | 4
4U_Koi_09 | Unwrap | A | 2 | 6
2D_Koi_09 | Texture | A | 2 | 4
5R_Koi_09 | Rigging | A | 2 | 4
6A_Koi_09 | Animation | A | 2 | 3
1C_Samurai_01 | Concept Art | B | 10 | 6
3D_Samurai_01 | Modeling | B | 10 | 9
4U_Samurai_01 | Unwrap | B | 10 | 6
2D_Samurai_01 | Texture | B | 10 | 8
5R_Samurai_01 | Rigging | B | 10 | 6
6A_Samurai_01 | Animation | B | 10 | 9
8SOU_Samurai_01 | Sound | B | 10 | 6
1C_Bandit_02 | Concept Art | B | 10 | 6
3D_Bandit_02 | Modeling | B | 10 | 8
4U_Bandit_02 | Unwrap | B | 10 | 5
2D_Bandit_02 | Texture | B | 10 | 7
5R_Bandit_02 | Rigging | B | 10 | 6
6A_Bandit_02 | Animation | B | 10 | 7
8SOU_Bandit_02 | Sound | B | 10 | 5
1C_Guard_03 | Concept Art | B | 8 | 5
3D_Guard_03 | Modeling | B | 8 | 7
4U_Guard_03 | Unwrap | B | 8 | 5
2D_Guard_03 | Texture | B | 8 | 7
5R_Guard_03 | Rigging | B | 8 | 5
6A_Guard_03 | Animation | B | 8 | 7
8SOU_Guard_03 | Sound | B | 8 | 5
1C_Warlord_04 | Concept Art | B | 10 | 8
3D_Warlord_04 | Modeling | B | 10 | 10
4U_Warlord_04 | Unwrap | B | 10 | 8
2D_Warlord_04 | Texture | B | 10 | 9
5R_Warlord_04 | Rigging | B | 10 | 6
6A_Warlord_04 | Animation | B | 10 | 10
8SOU_Warlord_04 | Sound | B | 10 | 8
1C_Demon_05 | Concept Art | B | 7 | 4
3D_Demon_05 | Modeling | B | 7 | 7
4U_Demon_05 | Unwrap | B | 7 | 5
2D_Demon_05 | Texture | B | 7 | 7
5R_Demon_05 | Rigging | B | 7 | 6
6A_Demon_05 | Animation | B | 7 | 7
8SOU_Demon_05 | Sound | B | 7 | 4
1C_Katana_01 | Concept Art | C | 10 | 1
3D_Katana_01 | Modeling | C | 10 | 3
4U_Katana_01 | Unwrap | C | 10 | 2
2D_Katana_01 | Texture | C | 10 | 2
8SOU_Katana_01 | Sound | C | 10 | 1
9P_Katana_01 | Particles | C | 10 | 4
1C_Shuriken_02 | Concept Art | C | 10 | 1
3D_Shuriken_02 | Modeling | C | 10 | 1
4U_Shuriken_02 | Unwrap | C | 10 | 1
2D_Shuriken_02 | Texture | C | 10 | 1
8SOU_Shuriken_02 | Sound | C | 10 | 2
9P_Shuriken_02 | Particles | C | 10 | 4
8SOU_SmokeBomb_03 | Sound | C | 9 | 2
1C_Kusarigama_04 | Concept Art | C | 10 | 2
3D_Kusarigama_04 | Modeling | C | 10 | 5
4U_Kusarigama_04 | Unwrap | C | 10 | 2
2D_Kusarigama_04 | Texture | C | 10 | 3
5R_Kusarigama_04 | Rigging | C | 10 | 3
6A_Kusarigama_04 | Animation | C | 10 | 6
8SOU_Kusarigama_04 | Sound | C | 10 | 5
9P_Kusarigama_04 | Particles | C | 10 | 6
1C_Nunchaku_05 | Concept Art | C | 6 | 1
3D_Nunchaku_05 | Modeling | C | 6 | 2
4U_Nunchaku_05 | Unwrap | C | 6 | 1
2D_Nunchaku_05 | Texture | C | 6 | 3
5R_Nunchaku_05 | Rigging | C | 6 | 1
6A_Nunchaku_05 | Animation | C | 6 | 5
8SOU_Nunchaku_05 | Sound | C | 6 | 3
9P_Nunchaku_05 | Particles | C | 6 | 5
1C_Fan_06 | Concept Art | C | 6 | 2
3D_Fan_06 | Modeling | C | 6 | 4
4U_Fan_06 | Unwrap | C | 6 | 3
2D_Fan_06 | Texture | C | 6 | 5
5R_Fan_06 | Rigging | C | 6 | 8
6A_Fan_06 | Animation | C | 6 | 6
8SOU_Fan_06 | Sound | C | 6 | 5
9P_Fan_06 | Particles | C | 6 | 5
1C_Dart_07 | Concept Art | C | 6 | 1
3D_Dart_07 | Modeling | C | 6 | 2
4U_Dart_07 | Unwrap | C | 6 | 1
2D_Dart_07 | Texture | C | 6 | 3
8SOU_Dart_07 | Sound | C | 6 | 3
9P_Dart_07 | Particles | C | 6 | 3
3D_DecKatana_08 | Modeling | C | 7 | 3
4U_DecKatana_08 | Unwrap | C | 7 | 2
2D_DecKatana_08 | Texture | C | 7 | 3
1C_BambooSword_09 | Concept Art | C | 7 | 1
3D_BambooSword_09 | Modeling | C | 7 | 3
4U_BambooSword_09 | Unwrap | C | 7 | 2
2D_BambooSword_09 | Texture | C | 7 | 3
1C_SmallKatana_10 | Concept Art | C | 4 | 1
3D_SmallKatana_10 | Modeling | C | 4 | 2
4U_SmallKatana_10 | Unwrap | C | 4 | 1
2D_SmallKatana_10 | Texture | C | 4 | 2
1C_ThrowingKnife_11 | Concept Art | C | 4 | 1
3D_ThrowingKnife_11 | Modeling | C | 4 | 1
4U_ThrowingKnife_11 | Unwrap | C | 4 | 1
2D_ThrowingKnife_11 | Texture | C | 4 | 2
1C_BoStaff_12 | Concept Art | C | 7 | 1
3D_BoStaff_12 | Modeling | C | 7 | 1
4U_BoStaff_12 | Unwrap | C | 7 | 1
2D_BoStaff_12 | Texture | C | 7 | 3
1C_House_01 | Concept Art | D | 10 | 5
3D_House_01 | Modeling | D | 10 | 10
4U_House_01 | Unwrap | D | 10 | 8
2D_House_01 | Texture | D | 10 | 10
3D_House_02 | Modeling | D | 10 | 10
4U_House_02 | Unwrap | D | 10 | 8
2D_House_02 | Texture | D | 10 | 10
3D_House_03 | Modeling | D | 5 | 10
4U_House_03 | Unwrap | D | 5 | 8
2D_House_03 | Texture | D | 5 | 10
3D_House_04 | Modeling | D | 5 | 10
4U_House_04 | Unwrap | D | 5 | 8
2D_House_04 | Texture | D | 5 | 10
1C_MarketStall_05 | Concept Art | D | 3 | 5
3D_MarketStall_05 | Modeling | D | 3 | 9
4U_MarketStall_05 | Unwrap | D | 3 | 8
2D_MarketStall_05 | Texture | D | 3 | 10
1C_Shrine_06 | Concept Art | D | 10 | 6
3D_Shrine_06 | Modeling | D | 10 | 8
4U_Shrine_06 | Unwrap | D | 10 | 6
2D_Shrine_06 | Texture | D | 10 | 7
1C_Prison_07 | Concept Art | D | 10 | 8
3D_Prison_07 | Modeling | D | 10 | 10
4U_Prison_07 | Unwrap | D | 10 | 9
2D_Prison_07 | Texture | D | 10 | 10
1C_Palace_08 | Concept Art | D | 10 | 10
3D_Palace_08 | Modeling | D | 10 | 10
4U_Palace_08 | Unwrap | D | 10 | 10
2D_Palace_08 | Texture | D | 10 | 10
1C_Dojo_09 | Concept Art | D | 8 | 8
3D_Dojo_09 | Modeling | D | 8 | 10
4U_Dojo_09 | Unwrap | D | 8 | 9
2D_Dojo_09 | Texture | D | 8 | 10
1C_Cottage_10 | Concept Art | D | 2 | 7
3D_Cottage_10 | Modeling | D | 2 | 9
4U_Cottage_10 | Unwrap | D | 2 | 6
2D_Cottage_10 | Texture | D | 2 | 8
1C_Torii_01 | Concept Art | E | 8 | 1
3D_Torii_01 | Modeling | E | 8 | 6
4U_Torii_01 | Unwrap | E | 8 | 3
2D_Torii_01 | Texture | E | 8 | 3
1C_StoneLantern_02 | Concept Art | E | 8 | 1
3D_StoneLantern_02 | Modeling | E | 8 | 3
4U_StoneLantern_02 | Unwrap | E | 8 | 2
2D_StoneLantern_02 | Texture | E | 8 | 2
3D_Crate_03 | Modeling | E | 3 | 1
4U_Crate_03 | Unwrap | E | 3 | 1
2D_Crate_03 | Texture | E | 3 | 1
1C_VilLantern_04 | Concept Art | E | 6 | 1
3D_VilLantern_04 | Modeling | E | 6 | 1
4U_VilLantern_04 | Unwrap | E | 6 | 1
2D_VilLantern_04 | Texture | E | 6 | 1
1C_StoneWall_05 | Concept Art | E | 8 | 4
3D_StoneWall_05 | Modeling | E | 8 | 5
4U_StoneWall_05 | Unwrap | E | 8 | 2
2D_StoneWall_05 | Texture | E | 8 | 3
1C_Sign_06 | Concept Art | E | 3 | 1
3D_Sign_06 | Modeling | E | 3 | 2
4U_Sign_06 | Unwrap | E | 3 | 1
2D_Sign_06 | Texture | E | 3 | 3
1C_SmallWoodenFence_07 | Concept Art | E | 5 | 2
3D_SmallWoodenFence_07 | Modeling | E | 5 | 3
4U_SmallWoodenFence_07 | Unwrap | E | 5 | 3
2D_SmallWoodenFence_07 | Texture | E | 5 | 2
1C_Bridge_08 | Concept Art | E | 9 | 8
3D_Bridge_08 | Modeling | E | 9 | 9
4U_Bridge_08 | Unwrap | E | 9 | 9
2D_Bridge_08 | Texture | E | 9 | 10
1C_SpirLantern_09 | Concept Art | E | 2 | 1
3D_SpirLantern_09 | Modeling | E | 2 | 1
4U_SpirLantern_09 | Unwrap | E | 2 | 1
2D_SpirLantern_09 | Texture | E | 2 | 1
1C_Flag_10 | Concept Art | E | 2 | 1
3D_Flag_10 | Modeling | E | 2 | 1
4U_Flag_10 | Unwrap | E | 2 | 1
2D_Flag_10 | Texture | E | 2 | 3
1C_PaperLantern_11 | Concept Art | E | 6 | 1
3D_PaperLantern_11 | Modeling | E | 6 | 1
4U_PaperLantern_11 | Unwrap | E | 6 | 1
2D_PaperLantern_11 | Texture | E | 6 | 1
3D_RagLine_12 | Modeling | E | 4 | 2
4U_RagLine_12 | Unwrap | E | 4 | 1
2D_RagLine_12 | Texture | E | 4 | 3
1C_Futon_13 | Concept Art | E | 1 | 1
3D_Futon_13 | Modeling | E | 1 | 1
4U_Futon_13 | Unwrap | E | 1 | 1
2D_Futon_13 | Texture | E | 1 | 3
3D_Bucket_14 | Modeling | E | 1 | 1
4U_Bucket_14 | Unwrap | E | 1 | 1
2D_Bucket_14 | Texture | E | 1 | 2
1C_FirePlace_15 | Concept Art | E | 3 | 2
3D_FirePlace_15 | Modeling | E | 3 | 4
4U_FirePlace_15 | Unwrap | E | 3 | 3
2D_FirePlace_15 | Texture | E | 3 | 3
3D_Bonsai_16 | Modeling | E | 2 | 7
4U_Bonsai_16 | Unwrap | E | 2 | 5
2D_Bonsai_16 | Texture | E | 2 | 7
1C_WoodenCage_17 | Concept Art | E | 7 | 3
3D_WoodenCage_17 | Modeling | E | 7 | 5
4U_WoodenCage_17 | Unwrap | E | 7 | 4
2D_WoodenCage_17 | Texture | E | 7 | 5
3D_Chain_18 | Modeling | E | 7 | 1
4U_Chain_18 | Unwrap | E | 7 | 1
2D_Chain_18 | Texture | E | 7 | 1
3D_Table_19 | Modeling | E | 6 | 2
4U_Table_19 | Unwrap | E | 6 | 1
2D_Table_19 | Texture | E | 6 | 2
3D_Candle_20 | Modeling | E | 6 | 1
4U_Candle_20 | Unwrap | E | 6 | 1
2D_Candle_20 | Texture | E | 6 | 1
3D_Chair_21 | Modeling | E | 4 | 2
4U_Chair_21 | Unwrap | E | 4 | 1
2D_Chair_21 | Texture | E | 4 | 2
1C_WallScroll_22 | Concept Art | E | 3 | 1
3D_WallScroll_22 | Modeling | E | 3 | 1
4U_WallScroll_22 | Unwrap | E | 3 | 1
2D_WallScroll_22 | Texture | E | 3 | 3
1C_Vase_23 | Concept Art | E | 1 | 1
3D_Vase_23 | Modeling | E | 1 | 1
4U_Vase_23 | Unwrap | E | 1 | 1
2D_Vase_23 | Texture | E | 1 | 2
1C_Statue_24 | Concept Art | E | 2 | 5
3D_Statue_24 | Modeling | E | 2 | 7
4U_Statue_24 | Unwrap | E | 2 | 4
2D_Statue_24 | Texture | E | 2 | 6
1C_PalLantern_25 | Concept Art | E | 4 | 1
3D_PalLantern_25 | Modeling | E | 4 | 1
4U_PalLantern_25 | Unwrap | E | 4 | 1
2D_PalLantern_25 | Texture | E | 4 | 1
1C_WallArt_26 | Concept Art | E | 3 | 5
3D_WallArt_26 | Modeling | E | 3 | 1
4U_WallArt_26 | Unwrap | E | 3 | 1
2D_WallArt_26 | Texture | E | 3 | 7
3D_Pillow_27 | Modeling | E | 2 | 1
4U_Pillow_27 | Unwrap | E | 2 | 1
2D_Pillow_27 | Texture | E | 2 | 2
3D_SittingTable_28 | Modeling | E | 3 | 2
4U_SittingTable_28 | Unwrap | E | 3 | 1
2D_SittingTable_28 | Texture | E | 3 | 2
1C_Pillar_29 | Concept Art | E | 5 | 1
3D_Pillar_29 | Modeling | E | 5 | 1
4U_Pillar_29 | Unwrap | E | 5 | 1
2D_Pillar_29 | Texture | E | 5 | 2
1C_DecoratedPillar_30 | Concept Art | E | 6 | 2
3D_DecoratedPillar_30 | Modeling | E | 6 | 3
4U_DecoratedPillar_30 | Unwrap | E | 6 | 2
2D_DecoratedPillar_30 | Texture | E | 6 | 4
1C_Throne_31 | Concept Art | E | 7 | 3
3D_Throne_31 | Modeling | E | 7 | 4
4U_Throne_31 | Unwrap | E | 7 | 2
2D_Throne_31 | Texture | E | 7 | 4
1C_Scroll_32 | Concept Art | E | 3 | 1
3D_Scroll_32 | Modeling | E | 3 | 1
4U_Scroll_32 | Unwrap | E | 3 | 1
2D_Scroll_32 | Texture | E | 3 | 2
1C_TeaSet_33 | Concept Art | E | 1 | 1
3D_TeaSet_33 | Modeling | E | 1 | 4
4U_TeaSet_33 | Unwrap | E | 1 | 3
2D_TeaSet_33 | Texture | E | 1 | 3
3D_SideTable_34 | Modeling | E | 2 | 1
4U_SideTable_34 | Unwrap | E | 2 | 1
2D_SideTable_34 | Texture | E | 2 | 1
1C_Dummy_35 | Concept Art | E | 6 | 1
3D_Dummy_35 | Modeling | E | 6 | 3
4U_Dummy_35 | Unwrap | E | 6 | 2
2D_Dummy_35 | Texture | E | 6 | 2
1C_WeaponRack_36 | Concept Art | E | 4 | 2
3D_WeaponRack_36 | Modeling | E | 4 | 3
4U_WeaponRack_36 | Unwrap | E | 4 | 2
2D_WeaponRack_36 | Texture | E | 4 | 3
1C_WallScrollPainting_37 | Concept Art | E | 3 | 2
3D_WallScrollPainting_37 | Modeling | E | 3 | 1
4U_WallScrollPainting_37 | Unwrap | E | 3 | 1
2D_WallScrollPainting_37 | Texture | E | 3 | 4
3D_Cave_01 | Modeling | F | 7 | 10
4U_Cave_01 | Unwrap | F | 7 | 10
2D_Cave_01 | Texture | F | 7 | 10
3D_Stone_02 | Modeling | F | 1 | 3
4U_Stone_02 | Unwrap | F | 1 | 3
2D_Stone_02 | Texture | F | 1 | 2
9P_Mist_01 | Particles | G | 0 | 0
9P_BlossomLeaves_02 | Particles | G | 3 | 4
9P_Smoke_03 | Particles | G | 4 | 0
9P_Water_04 | Particles | G | 7 | 0
9P_Fire_05 | Particles | G | 7 | 0
9P_HitStrike_06 | Particles | G | 10 | 8
9P_Blood_07 | Particles | G | 4 | 5
9P_Punch_08 | Particles | G | 6 | 5
9P_Jump_09 | Particles | G | 6 | 3
9P_Dragon_10 | Particles | G | 10 | 10
9P_Abilities_11 | Particles | G | 10 | 8
9P_SmokeBomb_12 | Particles | G | 8 | 2
1C_StartMenu_01 | Concept Art | H | 8 | 7
2D_StartMenu_01 | Texture | H | 8 | 7
1C_InGameMenu_02 | Concept Art | H | 7 | 9
2D_InGameMenu_02 | Texture | H | 7 | 9
1C_UI_03 | Concept Art | H | 10 | 10
2D_UI_03 | Texture | H | 10 | 10
1C_Inventory_04 | Concept Art | H | 6 | 9
2D_Inventory_04 | Texture | H | 6 | 9
1C_QuestLog_05 | Concept Art | H | 6 | 6
2D_QuestLog_05 | Texture | H | 6 | 6
1C_Map_06 | Concept Art | H | 7 | 5
2D_Map_06 | Texture | H | 7 | 5
1C_LoadingScreen_07 | Concept Art | H | 4 | 3
2D_LoadingScreen_07 | Texture | H | 4 | 3
6A_Intro_08 | Animation | H | 5 | 10
8SOU_Intro_08 | Sound | H | 5 | 10
6A_Temple_09 | Animation | H | 5 | 10
8SOU_Temple_09 | Sound | H | 5 | 10
6A_Dragon_10 | Animation | H | 5 | 10
8SOU_Dragon_10 | Sound | H | 5 | 10
6A_End_11 | Animation | H | 5 | 10
8SOU_End_11 | Sound | H | 5 | 10
7SCR_AI_01 | Script | I | 10 | 10
7SCR_PlayerController_02 | Script | I | 10 | 6
7SCR_Wallfade_03 | Script | I | 0 | 0
7SCR_LoadSave_04 | Script | I | 9 | 3
7SCR_Shrine_05 | Script | I | 5 | 2
7SCR_Settings_06 | Script | I | 4 | 4
7SCR_Events_07 | Script | I | 10 | 7
7SCR_EventManager_08 | Script | I | 10 | 7
7SCR_PlayerAttackManager_09 | Script | I | 10 | 8
7SCR_MusicSoundManager_10 | Script | I | 6 | 6
7SCR_MenuManager_11 | Script | I | 8 | 7
7SCR_LoadSaveManager_12 | Script | I | 10 | 4
7SCR_CombatManager_13 | Script | I | 8 | 6
7SCR_Coop_14 | Script | I | 1 | 10

## Blad2
Absenties
| 2016-09-12 | 2016-09-13 | 2016-09-15 | 2016-09-16
Victoria | ziek | ziek |  | 12:30 - 13:30
Jay
Wybren
Gerwin |  | tandarts 14:20 - 17:15 | ziek | ziek
René
Nathaly
Sprint 1 | 2016-09-19 | 2016-09-20 | 2016-09-22 | 2016-09-23 |  | 2016-09-26 | 2016-09-27 | 2016-09-29 | 2016-09-30
Victoria |  |  |  | 12:30 - 14:20 |  |  | 12:30 - 13:40 |  | 12:30 - 14:30
Jay
Wybren
Gerwin | [7 empty] | duim kapot
René
Nathaly
Sprint 2 | 2016-10-03 | 2016-10-04 | 2016-10-06 | 2016-10-07 |  | 2016-10-10 | 2016-10-11 | 2016-10-13 | 2016-10-14
Victoria |  |  |  | LAN Party |  |  |  |  | 12:30 - 14:00
Jay | ziek | ziek
Wybren |  |  |  | LAN Party
Gerwin |  |  |  | LAN Party
René | [6 empty] | ziek | ziek
Nathaly | [7 empty] | Diploma uitreiking zus
Vakantie
Sprint 3 | 2016-10-24 | 2016-10-25 | 2016-10-27 | 2016-10-28 |  | 2016-10-31 | 2016-11-01 | 2016-11-03 | 2016-11-04
Victoria
Jay
Wybren
Gerwin
René | ziek | ziek | ziek | ziek |  |  | ziek | tandarts 13:30 - 15:45
Nathaly |  | ziek | ziek | ziek |  |  | ziek
Sprint 4 | 7-11-2016 Studiedag | 2016-11-08 | 2016-11-10 | 2016-11-11 |  | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18
Victoria |  | ziek |  | 12:30 - 13:30 | [5 empty] | 12:30 - 13:45
Jay
Wybren
Gerwin
René
Nathaly | [5 empty] | ziek | ziek
DEADLINE | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25
Victoria
Jay | ziek
Wybren
Gerwin | ziek
René
Nathaly
Sprint 5 | 2016-11-28 | 2016-11-29 |  | 2016-12-01 | 2016-12-02 |  | 2016-12-05 | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09
Victoria
Jay
Wybren
Gerwin
René
Nathaly
Sprint 6 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 |  | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23
Victoria
Jay
Wybren
Gerwin
René
Nathaly
Vakantie
Sprint 7 | 2016-01-09 | 2016-01-10 | 2016-01-11 | 2016-01-12 | 2016-01-13 |  | 2016-01-16 | 2016-01-17 | 2016-01-18 | 2016-01-19 | 2016-01-20
Victoria
Jay
Wybren
Gerwin
René
Nathaly
DEADLINE | 2016-01-23 | 2016-01-24
Victoria
Jay
Wybren
Gerwin
René
Nathaly